## Project Tracker
PROJECT DELIVERY BREAKDOWN — Modules, Features & Timeline
Vaksindo · May 2026 · Platform: [Your Stack] · Period: [Date Range] · Tools: Windsurf, Claude
STATUS LEGEND: ✓ Done — Completed & live ⟳ In Progress — Currently being developed ⏸ Deferred — Planned, queued for future Date To = 'Ongoing' — Active work in progress Date = 'TBD' — Not yet scheduled
# | Module / Feature | Sub-item / Task | Status | Date From | Date To | Notes
1. PLATFORM FOUNDATION & ARCHITECTURE
1 | Project Platform | Initial app setup — framework, routing, base config | ✓ Done | 05 Jan 2026 | 20 Jan 2026 | Deployed at [your-url]
2 | Project Platform | Shared navigation component with responsive layout | ✓ Done | 15 Jan 2026 | 20 Jan 2026 | Persistent across all pages
3 | Project Platform | CI/CD deployment pipeline (e.g. Vercel / Netlify) | ✓ Done | 18 Jan 2026 | 20 Jan 2026 | Auto-deploy on push
4 | Module A | Feature specification & design document | ✓ Done | 01 Feb 2026 | 03 Feb 2026
5 | Module A | Core feature implementation | ⟳ In Progress | 03 Feb 2026 | Ongoing | Currently in Windsurf
2. CORE MODULE — [YOUR MODULE NAME]
6 | [Module Name] | Database schema design & seed data | ✓ Done | 10 Feb 2026 | 12 Feb 2026
7 | [Module Name] | API / backend logic implementation | ✓ Done | 12 Feb 2026 | 15 Feb 2026
8 | [Module Name] | UI component build — list, detail, form views | ⟳ In Progress | 15 Feb 2026 | Ongoing | Prompt prepared for Windsurf
9 | [Module Name] | Translation / localisation (EN/ID/VI) | ⏸ Deferred | TBD | TBD | Dedicated session queued
3. [SECONDARY MODULE]
10 | [Secondary Module] | Concept design & integration spec | ✓ Done | 01 Mar 2026 | 03 Mar 2026
11 | [Secondary Module] | Calculator / logic engine implementation | ✓ Done | 03 Mar 2026 | 10 Mar 2026 | Core engine live
12 | [Secondary Module] | Translation audit — all strings | ⏸ Deferred | TBD | TBD | Queued after main module
4. PLANNED FEATURES & ROADMAP
13 | Roadmap | Feature X — specification complete, build TBD | ⏸ Deferred | TBD | TBD | Next priority
14 | Roadmap | Feature Y — longer horizon v2.0 concept | ⏸ Deferred | TBD | TBD | Concept only
5. DOCUMENTATION, COMMUNICATIONS & MARKETING
15 | Documentation | User Guide — all modules, FAQ, appendices | ✓ Done | 23 Mar 2026 | 25 Mar 2026 | 50+ pages
16 | Communications | Launch announcement email — stakeholders | ✓ Done | 24 Mar 2026 | 25 Mar 2026
17 | Marketing | Marketing materials — slides, bullet points | ⏸ Deferred | TBD | TBD
— End of Document —

## 📋 How to Use
📋 DailyFlow Pro — Import Template Instructions
COLUMNS EXPLAINED
# | Sequential row number (1, 2, 3…). Auto-fill or enter manually.
Module / Feature | The parent module or feature group. e.g. 'FarmGuide', 'Biosecurity — Poultry'. Tasks sharing the same module will be grouped into one Project in DailyFlow Pro.
Sub-item / Task | Specific task or deliverable within the module. Be descriptive — this becomes the Task Title in the app.
Status | Must be exactly one of: ✓ Done ¦ ⟳ In Progress ¦ ⏸ Deferred (Use the dropdown in column D — Sheet 1)
Date From | Start date. Format: DD Mon YYYY (e.g. 05 Jan 2026) or YYYY-MM-DD. Use 'TBD' if not scheduled yet.
Date To | End date. Same format as Date From. Use 'Ongoing' for active work, 'TBD' for unscheduled.
Notes | Optional context: sources, decisions, blockers, links, tool used (e.g. Windsurf, Claude).
SECTION ROWS
How to add | Insert a row and merge cells A:G. Fill with a dark green background and white bold text (match existing section style). Section rows are NOT imported as tasks — they are visual groupings only.
IMPORT BEHAVIOUR
Projects | The app reads the 'Module / Feature' column. All rows sharing the same module name → grouped under one Project record in Supabase.
Tasks | Each data row → one Task record linked to its parent Project.
Progress % | Auto-calculated after import: (Done tasks ÷ Total tasks) × 100.
Duplicates | If a Project with the same name already exists in the app, new tasks are appended to it (no duplicate project created).
Skipped rows | Section header rows (merged cells), empty rows, and rows with missing Module or Task fields are skipped and shown in the import preview.
TIPS
Do not rename columns | The app parser expects the 7-column layout in exact order. Do not insert, remove, or reorder columns.
Multiple sheets | Only the first sheet ('Project Tracker') is imported. This README sheet is ignored.
File format | Save as .xlsx or .csv before uploading. .xls (legacy) is not supported.
Section rows | You may add or remove section rows freely — they are purely visual and will not affect the import.