## Project
Field Name | Type | Fungsi | Contoh Value
`Project ID` | Text/Formula | Unique identifier | `PRJ-001`
`Project Name` | Title | Nama proyek | "Website Redesign"
`Parent Project` | Relation | Link ke project induk (jika ada) | -
`Status` | Select | Status keseluruhan | `Planning` / `In Progress` / `Done`
`Start Date` | Date | Tanggal mulai | `2026-05-01`
`Due Date` | Date | Deadline proyek | `2026-08-31`
`Progress %` | Rollup/Formula | % penyelesaian (dari task) | `75%`
`Total Tasks` | Rollup | Jumlah task terkait | `45`
`Completed Tasks` | Rollup | Task yang selesai | `32`
`Effort Estimate` | Number | Estimasi effort (jam/story points) | `120`
`Actual Effort` | Rollup | Realisasi effort dari task | `98`
`Priority` | Select | Prioritas bisnis | `High` / `Medium` / `Low`
`Owner` | Person | Penanggung jawab | `@user`

## Sub Project
Field Name | Type | Fungsi | Contoh Value
`SubProject ID` | Text/Formula | Unique identifier | `SUB-001-A`
`SubProject Name` | Title | Nama sub-proyek | "UI/UX Design Phase"
`Parent Project` | Relation | ⭐ **Wajib**: Link ke Project | `PRJ-001`
`Status` | Select | Status sub-proyek | `In Progress`
`Start/End Date` | Date | Timeline spesifik | `2026-05-15` → `2026-06-30`
`Progress %` | Rollup | % dari task child | `60%`
`Task Count` | Rollup | Jumlah task di bawahnya | `18`
`Completed Count` | Rollup | Task selesai | `11`
`Effort Estimate` | Number | Estimasi effort sub-proyek | `45`
`Actual Effort` | Rollup | Realisasi dari task | `38`
`Dependencies` | Relation | Link ke sub-project lain yang jadi prasyarat | `SUB-001-B`

## Tasks
Field Name | Type | Fungsi | Contoh Value
`Task ID` | Text/Formula | Unique identifier | `TSK-001-A-03`
`Task Name` | Title | Deskripsi tugas | "Buat wireframe homepage"
`Parent Project` | Relation | ⭐ **Wajib**: Link ke Project | `PRJ-001`
`Parent SubProject` | Relation | ⭐ **Wajib**: Link ke Sub-Project | `SUB-001-A`
`Status` | Select | Status task | `To Do` / `Doing` / `Done` / `Blocked`
`Priority` | Select | Prioritas eksekusi | `P0` / `P1` / `P2`
`Assignee` | Person | Penanggung jawab | `@designer`
`Due Date` | Date | Deadline task | `2026-05-20`
`Estimated Time` | Number | Estimasi durasi (jam) | `4`
`Actual Time` | Number | Realisasi waktu | `3.5`
`Completion %` | Number | Progres task (untuk task multi-step) | `100`
`Tags` | Multi-select | Kategori/label | `Design` / `Frontend` / `Review`
`Related Notes` | Relation | Link ke notes/comments | `NOTE-045`
`Is Blocker` | Checkbox | Apakah task ini menghambat yang lain? | `✓`

## Notes_Comments
Field Name | Type | Fungsi | Contoh Value
`Note ID` | Text/Formula | Unique identifier | `NOTE-045`
`Note Title` | Title | Judul catatan | "Feedback Wireframe v1"
`Related Project` | Relation | Link ke Project | `PRJ-001`
`Related SubProject` | Relation | Link ke Sub-Project | `SUB-001-A`
`Related Task` | Relation | Link ke Task spesifik | `TSK-001-A-03`
`Note Type` | Select | Kategori catatan | `Feedback` / `Meeting Notes` / `Reference` / `Decision`
`Created Date` | Date | Waktu pembuatan | `2026-05-18 14:30`
`Author` | Person | Penulis catatan | `@user`
`Visibility` | Select | Siapa yang bisa lihat | `Team` / `Private` / `Public`
`Is Actionable` | Checkbox | Apakah catatan ini perlu jadi task? | `✓`
`Linked Action Task` | Relation | Jika actionable, link ke task baru | `TSK-001-A-07`

## Formula
Ratio | Rumus | Interpretasi
**Project Completion** | `Completed Tasks / Total Tasks × 100` | % penyelesaian proyek
**Time Efficiency** | `Estimated Time / Actual Time × 100` | >100% = lebih cepat, <100% = molor
**Task Density** | `Total Tasks / Project Duration (days)` | Beban kerja per hari
**Blocker Impact** | `Blocked Tasks / Total Tasks × 100` | % task terhambat
**Note-to-Action Rate** | `Actionable Notes / Total Notes × 100` | Efektivitas dokumentasi